## Function Request
Orthotic Work order and Lab (OWL) Program | [9 empty] | 2026-07-31
Function Request | DATE OF REQUEST | REQUESTOR | DESCRIPTION | GUI VER | PATCH NUM | ASSIGNED | ASSIGNED DATE | % COMPL | COMPL DATE | REMARKS
1 | 2005-03-23 |  | Use Purchase Order Screen as process start point | 6 | 75 | Ken | 2005-03-23 | 100 | 2005-10-26
2 | 2005-03-23 |  | P.A determins TYPE - Orthotics/Prosthetics, Optical, Restoration. Wheelchair | 6 | 75 | Ken, Sam | 2005-03-23 | 100 | 2005-10-26
3 | 2005-03-23 |  | P.A completes the creation of LWO | 6 | 75 | Ken, Sam | 2005-03-23 | 100 | 2005-10-26
4 | 2005-03-23 |  | LWO display must be sortable | 6 | 75 | Ken, Sam | 2005-03-23 | 50
5 | 2005-03-23 |  | P.A can post note to CPRS at creation | 6 | 75 | Ken, Sam | 2005-03-23 | 100 | 2005-11-13 | Removed 11/17/2005 per FR36
6 | 2005-03-23 |  | LWO is a smart number w/month & FY | 6 | 75 | Sam | 2005-03-23 | 100
7 | 2005-03-23 |  | LWO number will use month |  |  | Sam | 2005-03-23 |  |  | Set for furture version.
8 | 2005-03-23 |  | View CPRS capability | 6 | 75 | Ken | 2005-03-23 | 100 | 2005-11-23
9 | 2005-03-23 |  | View Request capability | 6 | 75 | Ken | 2005-03-23 | 100 | 2005-11-23
10 | 2005-03-23 |  | Description displays | 6 | 75 | Ken | 2005-03-23
11 | 2005-03-23 |  | Tech can post a Note to CPRS |  |  | Ken | 2005-03-23
12 | 2005-03-23 |  | Include Site - Local or IFC
13 | 2005-03-23 |  | Work Order prints at P.A. creation | 6 | 75 |  | 2005-03-23 |  |  | Also see FR24
14 | 2005-03-23 |  | Can select Billing Item | 6 | 75 | Ken | 2005-03-23 | 100 | 2005-10-26
15 | 2005-03-23 |  | Can select HCPCS - NIF | 6 | 75 | Ken | 2005-03-23 | 100 | 2005-10-26
16 | 2005-03-23 |  | Component cost capture | 6 | 75
17 | 2005-03-23 |  | NPPD costs not duplicated | 6 | 75
18 | 2005-03-23 |  | Account for depreciation
19 | 2005-03-23 |  | Assign tech to LWO | 6 | 75
20 | 2005-03-23 |  | Labor hours in qtr hours | 6 | 75
21 | 2005-03-23 |  | Purchase from LWO
22 | 2005-03-23 |  | LWO can be edited | 6 | 75
23 | 2005-03-23 |  | LWO can be cancelled | 6 | 75
24 | 2005-03-23 |  | Print LWO - Options including VistA Printers | 6 | 75 | Ken | 2005-03-23 |  |  | Also see FR13
25 | 2005-03-23 |  | Origin includes - Purchase Stock or Used | 6 | 75
26 | 2005-03-23 |  | High Tech Item ID'd by tech | 6 | 75
27 | 2005-03-23 |  | Material and Labor can be edited with checks
28 | 2005-03-23 |  | Use of Item Kits
29 | 2005-03-23 |  | Bar code eyeglasses
30 | 2005-08-25 |  | View 2319 to show lab detail
31 | 2005-10-03 |  | P.A at create LWO can enter sending and receiving station ID. Work for other sites. | 6 | 75 | Ken, Sam | 2005-10-03 | 100
32 | 2005-10-27 |  | Add two additional custom display fields for NPPD display program | 6 | 75 | Ken, Helen | 2005-10-27 | 100 | 2005-11-22
33 | 2005-11-07 |  | Suspense record remains in the POC screen after Creation of Work Order until POC screen is refreshed or closed. | 6 | 75 | Ken | 2005-11-07 | 100 | 2005-11-16
34 | 2005-11-07 |  | Add check box in POC screen to display LAB type in POC screen. |  |  | Ken, Sam |  |  |  | Remove - not needed
35 | 2005-11-07 |  | Default Primary Item Description with Unit of Issue = Each, and QTY = 1. | 6 | 75 | Ken | 2005-11-07 | 100 | 2005-11-16 | Removed VoI: see FR38
36 | 2005-11-17 |  | Remove the functionality that was requested in FR5. | 6 | 75 | Ken | 2005-11-17
37 | 2005-11-17 |  | Add auto posting of default ‘Note to CPRS’, based on Lab Type selection | 6 | 75
38 | 2005-11-17 |  | Remove the Unit of Issue selection and replace with default -> Job | 6 | 75 | Ken | 2005-11-17 | 100 | 2005-11-23
39 | 2005-11-17 |  | Add logic to prevent closing of Lab Order from GUI Purchasing | 6 | 75
40 | 2006-01-05 |  | Auto note to CPRS will be either: Wheelchair – Repair ¦ Restoration – Lab ¦ Prosthetic/Orthotic Lab ¦ Eyeglass | 6 | 75
41 | 2006-01-05 |  | ICD-9 codes field view expanded | 6 | 75
42 | 2006-01-05 |  | Need modifier for RIGHT or LEFT; mandatory for orthotics and restoration | 6 | 75